## UAT Checklist Instructions
Instructions for Query Connector UAT Checklist
This document is your guide for performing User Acceptance Testing (UAT) for Query Connector. Your goal is to ensure the application functions as intended.
1. General Functionality: Use the General Functionality checklist to test the basic access and navigation of Query Connector.
2. Admin and Super Admin Testing: Use the Admin and Super Admin checklist to verify whether administrative functions for these roles are working as expected, including query building, code management, audit logs, and FHIR server configuration. For each item, record a status of Yes (if it works as described), No (if it doesn't work or acts unexpectedly), or Not Applicable, and any relevant notes.
3. End-to-end Query Test: Use the End-to-end Query checklist to test the patient querying process from start to finish, ensuring data flows correctly through the UI. For each item, record a status of Yes (if it works as described), No (if it doesn't work or acts unexpectedly), or Not Applicable, and any relevant notes.

## 1. General Functionality Test
Use this sheet when testing the basic access and navigation of Query Connector.
Acceptance Criteria | Yes/No/NA | Notes
You can sign in successfully with your provided credentials
The application loads without errors
Navigation menu and buttons are responsive to clicks
Queries are visible and populated

## 2. Admin and Super Admin Test
Use this sheet to test administrative functions by role, including query building, code management, audit logs, and FHIR server configuration.
Acceptance Criteria | Yes/No/NA | Notes
Query Building
Option 1 - Upload CSV via the Code Library
You can navigate to the Code library
You can download a sample CSV using the "Download sample CSV" link
You can reformat the CSV table with relevant ICD-10 and SNOMED CT codes and upload the CSV
Searching for codes (e.g., PCOS) returns expected matches
Option 2 - Manual code entry via the Code Library
You can navigate to the Code library
You can add specific value sets/codes
Entering Code: E28.2 (ICD-10) and Name: Polycystic ovarian syndrome creates a valid row
Entering Code: 69878008 (SNOMED CT) and Name: Polycystic ovaries creates a valid row.
Searching for codes (e.g., PCOS) returns expected matches
Option 3 - Build on-the-fly via the Query Repository
You can navigate to the Query repository
You can input a query name and create a query from scratch
You can navigate to the Code library via the "manage codes" link
You can add specific value sets/codes via CSV upload or manual code entry
Saved queries are available in the Query Repository
Code Library
You can view all existing value sets and see their included codes
You can edit value sets you created and are restricted from editing others
Audit Log
Audit log entries appear immediately after users run queries or build queries
Search/filter by user action and date range works as expected
Entries are understandable (who did what when)
Access Management
Permission levels (Standard/Admin/Super Admin) can be assigned to users
User groups can be created and memberships modified
Confirm group members can only see queries assigned to them
FHIR Configuration
The configured server (e.g. OpenEpic: eHealthExchange) is selectable
FHIR server is successfully connected after testing the connection

## 3. End-to-End Query Test
Use this sheet to verify the full "Run a Query" workflow, from entering patient data to viewing the final patient results.
Acceptance Criteria | Yes/No/NA | Notes
Name + DOB + one ID (MRN, phone, or address) can be entered
Under 'Advanced', the HCO field is set to the correct test server (e.g., OpenEpic: eHealthExchange)
Clicking 'Search for Patient' proceeds without system errors
Known test patients appear in the match list
Selecting a patient advances you to query selection
Expected queries are visible based on your role/group permissions
Selecting a query and clicking 'Submit' works successfully
Results load on the Patient Record page successfully
Sidebar navigation within the patient record works as expected
Patient Info, Observations, Conditions, Encounters, and Meds appear (as applicable)
"View FHIR response" loads the full JSON bundle correctly